| Harvard ManageMentor — SETTING GOALS TOOLS |  |  |
| --- | --- | --- |
| Goal and Task Chart |  |  |
| List the tasks associated with each of your goals and include the time frame, resources needed, potential obstacles, measured outcomes, and milestones for each task. |  |  |
| Goal (objective): Improve coordination (linkages) with scholarship programs to promote careers and career development |  |  |
| Payoff: Improved retention and recruitment |  |  |
| Task 1: | Time Frame: | Resources: |
| Identify scholarships and grant support from national, state, regional and foreign resources | Before end of fall semester 2006 | Human resources (2 people agriculture & marine resources (.1 FTE)) |
| Obstacles: | Measured Outcomes: | Milestones: |
| Sharing of information – regular contact Person not qualified to accomplish task – Multiple sources Coordination and information sharing for careers – Develop dissemination plan for the information Processing time by lenders – know timelines | Listing of scholarships by spring semesters and information available for counselors and advisors | Identify key local contacts for scholarships – 2 weeks from today |
| © 1998 by the President and Fellows of Harvard College and its licensors. All rights reserved. |  |  |

| Harvard ManageMentor — SETTING GOALS TOOLS |  |  |
| --- | --- | --- |
| Goal and Task Chart |  |  |
| List the tasks associated with each of your goals and include the time frame, resources needed, potential obstacles, measured outcomes, and milestones for each task. |  |  |
| Goal (objective): Move to learning centered programs |  |  |
| Payoff: More effective (high level of learning and achievement/high retention and graduation) programs |  |  |
| Task 1: | Time Frame: | Resources: |
| Review/revise programs for learner-centeredness which reflects learning styles of our students | One year 2007 | Program Faculty and ICs Program and Course Learning Outcome documents |
| Obstacles: | Measured Outcomes: | Milestones: |
| Different levels of understanding in embracing learner-centeredness Resources | Satisfaction that program is meeting their learning styles and needs | Survey completed end of 2007 |
| © 1998 by the President and Fellows of Harvard College and its licensors. All rights reserved. |  |  |

| Harvard ManageMentor — SETTING GOALS TOOLS |  |  |
| --- | --- | --- |
| Goal and Task Chart |  |  |
| List the tasks associated with each of your goals and include the time frame, resources needed, potential obstacles, measured outcomes, and milestones for each task. |  |  |
| Goal (objective): Improve Articulation with post-secondary institutions |  |  |
| Payoff: Improved academic quality of exiting/transferring students |  |  |
| Task 1: | Time Frame: | Resources: |
| Identify 4-yr institutions and programs that we want articulation | End of October 2006 | Chairs/Key Faculty/VPIA |
| Obstacles: | Measured Outcomes: | Milestones: |
| None so far | Institutions and programs identified | List of programs and universities and current MOUs/articulation agreements |
| Task 2: | Time Frame: | Resources: |
| (Re)establish key contacts in identified programs and institutions | end of November 2006 | Chairs to establish contact/ |
| Obstacles: | Measured Outcomes: | Milestones: |
| None so far | Contact names/addresses/websites/exchange of curricula/course outlines | Mutual review of programs |
| Task 3: | Time Frame: | Resources: |
| Preparation and approval of MOUs/articulation agreements | end of March 2007 for Marine Science and end of May 2007 for Agriculture | DAP/VPIA to prepare MOU |
| Obstacles: | Measured Outcomes: | Milestones: |
| Time consuming | Signed agreements in place | Final drafts by mid-Feb 2007 for March BOR meeting and mid-April for May BOR meeting |
| © 1998 by the President and Fellows of Harvard College and its licensors. All rights reserved. |  |  |

| Harvard ManageMentor — SETTING GOALS TOOLS |  |  |
| --- | --- | --- |
| Goal and Task Chart |  |  |
| List the tasks associated with each of your goals and include the time frame, resources needed, potential obstacles, measured outcomes, and milestones for each task. |  |  |
| Goal (objective): Improve Articulation with secondary schools |  |  |
| Payoff: Improved academic quality of incoming and exiting/transferring students |  |  |
| Task 1: | Time Frame: | Resources: |
| Create TF to align curriculum with high schools | Two months (end November 2006) | VPIA/DAP/DCR/IC-KSA/Chairs/State DOE/Sc/Ag Spec |
| Obstacles: | Measured Outcomes: | Milestones: |
| Resistance from DOE - “work” on Director | TF members identified and confirmed | TF formed and one initial meeting by the end of November 2006 |
| Task 2: | Time Frame: | Resources: |
| TF to examine and identify areas that need to be aligned in the curriculum | end of Spring 2007 (end May) | Copies of curricula and course outlines; textbooks HR: TF +Ag and Sc Instructors |
| Obstacles: | Measured Outcomes: | Milestones: |
| - Gathering appropriate documents - Scheduling times for meetings | Identify disparities and plan to close these | Summary report and action plan developed |
| Task 3: | Time Frame: | Resources: |
| Approval and Implement the plan | start Fall 2007 | Small budget for meetings/workshops |
| Obstacles: | Measured Outcomes: | Milestones: |
| - Resistance to the plan - Possibility of huge capacity building backlog/limited educational expertise | Aligned curriculum | Approval of the plan |
| © 1998 by the President and Fellows of Harvard College and its licensors. All rights reserved. |  |  |